#### Form TASK

|  |  |  |  |
| --- | --- | --- | --- |
| Name | E-commerce | Date | 2018-03-06 |
| Team | Savana | Instructor | Saulius Ragaišis |
| Part/Level | 1 | Cycle | 1 |

|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | | | | **Plan Hours** | | | | | | | **Plan Size/Value** | | | | | **Actual** | | |
| Phase | Part | Task Name | # Engineers | Team Leader | Development Manage | Planning Manager | Qual./Proc. Manager | Support Manager | Total Team Hours | Cumulative  Hours | Size Units | Size | Week No. | Planned Value | Cumulative  PV | Hours | Cumulative Hours | Week No. |
| D | PRP | Environment setup | 5 | 1 | 1 | 1 | 1 | 1 | 5 | 5 |  |  | 1 | 4 | 4 |  |  |  |
| D | PR | Setup MVC structure | 1 |  |  | 1 |  |  | 1 | 6 | 50 |  | 1 | 1 | 5 |  |  |  |
| D | M | Home page | 1 |  |  |  |  | 2 | 2 | 8 | 500 |  | 2 | 2 | 7 |  |  |  |
| D | ITM | Items list page | 2 |  | 3 |  | 4 |  | 7 | 15 | 300 |  | 3 | 6 | 13 |  |  |  |
| D | ITM | Item details page | 2 |  | 2 |  | 1 |  | 3 | 18 | 150 |  | 3 | 3 | 16 |  |  |  |
| D | M | Integrate database | 1 | 2 |  |  |  |  | 2 | 20 | 50 |  | 4 | 2 | 18 |  |  |  |
| D | ITM | Add item function | 3 | 1 |  | 5 |  | 2 | 8 | 28 | 100 |  | 4 | 7 | 25 |  |  |  |
| D | ITM | Update item function | 3 | 2 |  | 3 |  | 2 | 7 | 35 | 50 |  | 5 | 6 | 31 |  |  |  |
| D | ITM | Delete item function | 1 |  |  |  |  | 2 | 2 | 37 | 50 |  | 6 | 2 | 33 |  |  |  |
| D | AUT | Authentication | 3 | 3 | 2 |  | 2 |  | 7 | 44 | 150 |  | 7 | 6 | 39 |  |  |  |
| D | SCT | Shopping cart | 3 |  | 6 | 2 | 4 |  | 12 | 56 | 400 |  | 8 | 10 | 49 |  |  |  |
| D | ADM | Admin page | 2 | 5 |  |  |  | 5 | 10 | 66 | 300 |  | 9 | 8 | 57 |  |  |  |
| D | AUT | Customer registration | 2 |  | 3 |  | 2 |  | 5 | 71 | 200 |  | 10 | 4 | 61 |  |  |  |
| D | M | REST services | 3 | 1 |  | 3 |  | 3 | 7 | 78 | 150 |  | 11 | 6 | 67 |  |  |  |
| D | ADM | Manage orders | 2 |  |  | 6 | 5 |  | 11 | 89 | 400 |  | 12 | 10 | 77 |  |  |  |
| R | PRP | Review requirements | 2 | 1 |  |  |  | 4 | 5 | 94 |  |  | 1 | 4 | 81 |  |  |  |
| T | MNT | Write useful forms, protocols and/or documentation | 5 | 2 | 2 | 2 | 2 | 2 | 10 | 104 |  |  | 6,8,12 | 8 | 88 |  |  |  |
| R | MNT | Communicate with the client | 1 | 3 |  |  |  |  | 3 | 107 |  |  | 1-12 | 2 | 91 |  |  |  |
| T | M | Test the system | 5 | 3 | 2 | 2 | 2 | 3 | 12 | 119 |  |  | 1-12 | 10 | 100 |  |  |  |